## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-10-17 | 2022-10-18 | 2022-10-19
|  | Day 0 | Day 1 | Day 2 | Day 3
1 | Identify #1 GoF design pattern | 2 |  | 1 | 1
2 | Identify #2 GoF design pattern | 2 |  | 1 | 1
3 | Identify #3 GoF design pattern | 2 |  | 1 | 1
4 | Identify #4 GoF design pattern | 2 |  |  | 2
5 | Identify #5 GoF design pattern | 2 |  |  | 2
6 | Identify #6 GoF design pattern | 2 |  |  | 2
7 | Identify #7 GoF design pattern | 2 |  | 1 | 1
8 | Identify #8 GoF design pattern | 2 |  | 1 | 1
9 | Identify #9 GoF design pattern | 2 |  |  | 2
10 | Identify #10 GoF design pattern | 2 |  |  | 2
11 | Identify #11 GoF design pattern | 2 |  |  | 2
12 | Identify #12 GoF design pattern | 2 |  |  | 2
13 | Identify #13 GoF design pattern | 2 |  |  | 2
14 | Identify #14 GoF design pattern | 2 |  |  | 2
15 | Identify #15 GoF design pattern | 2 |  |  | 2
Completed Effort |  | 0 | 0 | 5 | 25
Remaining Effort |  | 30 | 30 | 25 | 0
Ideal Burndown |  | 30 | 20 | 10 | 0