## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-10-17 | 2022-10-18 | 2022-10-19
|  | Day 0 | Day 1 | Day 2 | Day 3
1 | Identify #1 code smell | 1 |  |  | 1
2 | Identify #2 code smell | 1 |  |  | 1
3 | Identify #3 code smell | 1 |  |  | 1
4 | Identify #4 code smell | 1 |  |  | 1
5 | Identify #5 code smell | 1 |  |  | 1
6 | Identify #6 code smell | 1 |  |  | 1
7 | Identify #7 code smell | 1 |  |  | 1
8 | Identify #8 code smell | 1 |  |  | 1
9 | Identify #9 code smell | 1 |  |  | 1
10 | Identify #10 code smell | 1 |  |  | 1
11 | Identify #11 code smell | 1 |  |  | 1
12 | Identify #12 code smell | 1 |  |  | 1
13 | Identify #13 code smell | 1 |  |  | 1
14 | Identify #14 code smell | 1 |  |  | 1
15 | Identify #15 code smell | 1 |  |  | 1
Completed Effort |  | 0 | 0 | 0 | 15
Remaining Effort |  | 15 | 15 | 15 | 0
Ideal Burndown |  | 15 | 10 | 5 | 0