## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-10-31 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Search possible funcionalities to implement | 1 |  | 0.5 |  |  | 0.5
2 | Search possible funcionalities to implement | 1 |  |  | 1
3 | Search possible funcionalities to implement | 1 |  | 0.5 |  |  | 0.5
4 | Search possible funcionalities to implement | 1 |  |  |  | 1
5 | Search possible funcionalities to implement | 1 |  |  |  | 1
6 | Search possible funcionalities to implement | 1 |  |  |  |  | 1
7 | Search possible funcionalities to implement | 1 |  |  |  |  | 1
8 | Search possible funcionalities to implement | 1 |  |  |  | 1
9 | Search possible funcionalities to implement | 1 |  |  |  |  | 1
10 | Search possible funcionalities to implement | 1 |  |  |  |  | 1
Completed Effort |  | 0 | 0 | 1 | 1 | 3 | 5
Remaining Effort |  | 10 | 10 | 9 | 8 | 5 | 0
Ideal Burndown |  | 10 | 8 | 6 | 4 | 2 | 0